RURAL VIOLENCE AGAINST WOMEN: THE TIME IS NOW FOR CHANGE AND ACTION!

Action items from 4 community meetings held in April 2016

| Issue | Strategy | Next steps | Person/organization responsible | Timeline | Comments |
| --- | --- | --- | --- | --- | --- |
| General | Establish an eastern Ontario rural VAW Coalition | Apply for funds through Rural Realities | Erin/planning committee for rural meetings | Immediate: April 29 | Coalition would be cross-sectoral and would do policy reform advocacy, oversee/plan joint training, establish and maintain an online tools and resources clearinghouse |
|  | Use of $17,000 | Decision to be made about how to spend | Erin, Sue and Leigh | Short term |  |
|  | Establish group email list | Sue, Erin and Bev to send lists from each meeting to Karen Smith | Karen to establish list and provide to all attendees and organizers | As soon as possible |  |
| Distance | Cross-county transportation strategy | Gather and circulate research being done in Lanark County | Jane (Lanark councillor) to circulate information and organize first meeting of working group | By end June | Group will consider research and identify ideas: gas tax, school buses, Uber, pooled funding etc. |
| Services | Cross-county crisis response model | Discussions at coordinating committee level | Lanark: Brie L & A: Sue Renfrew: Bev and BMH |  | To look at communication, information sharing, process for responding to crisis in small and rural communities |
|  | Mandated collaboration | Take to VAW Roundtable and Building a Bigger Wave | Pam | By end June | To ensure all key players are at the tables they need to be at |
|  | Invest in prevention | Take to VAW Roundtable | Pam | By end June | Most agencies doing prevention work have no funding to do so |
| Women’s safety | Work with OW system | Discussions within OW Training for OW staff | Renfrew: Brenda Lanark: Julie G L & A: Sue to find | Ongoing | Have one designated, specially trained VAW staff in each OW office to respond appropriately to women (eg flowing money before woman leaves abuser). |
|  |  | Addressing policy issues with OW system | As above | As above | Changing policies that do not enhance women’s safety |
|  | Increase safe access to information and support for women | Building service hubs | Jane to share Lanark County survey re unused space in county |  | So women can access information, support and services in locations they already go to: schools, health centres, farmers’ markets, rural events, festivals |
|  |  | Explore alternative ways to share information with women |  |  | Info in public bathroom stalls |
|  | Expanded use of situation tables |  | Lanark to share with Renfrew |  |  |
| Community Engagement and empowerment | Public education | Conduct an inventory of existing public education with a rural focus | Julie Lalonde and Brianne to lead | Immediate | Bystander engagement, knowledge and skills building |
|  | Engaging local and county councils | VAW sectors to reach out to local and county councils | All, with ideas and support from Erin | Start now, ongoing | Work towards having VAW information a regular part of council meetings |
| Education | Prevention education in schools | Inventory of existing curriculum | Julie Lalonde | Immediate | Look at existing models (eg Roots of Empathy) as well as old programs (eg VIP). |
|  |  |  |  |  | Build new curriculum where needed (eg How to apply VAW First Aid) |
|  |  |  |  |  | Build on new sex ed curriculum because it is mandatory |
|  |  |  |  |  | Engage with parent councils and school boards |
| Legal systems | Address perpetrator release process/criteria | Advocate for policy/regulation changes | Coordinating committees to write letters to VAW Roundtable, Pam to provide support | immediate | Change so women’s safety is top not bottom priority in determining bail, probation conditions etc. |
|  |  |  |  |  | Revise offender release notification system |
|  | Establish rural specialized domestic violence courts | Advocate with Attorney General | Stephanie to discuss with local Justice Erin to approach her County Council to set up meeting with AG at August provincial council gathering | Immediate and ongoing |  |
|  | Enhance court supports for survivors of VAW | Increase resourcing for Family Court Support Worker Program |  |  |  |
|  |  | Create FCSW model for criminal court |  |  |  |
|  | Create accountability for legal system | Court Watch program | Bev to lead |  | Contact WomenatthecentrE re its Court Watch program – perhaps become part of the pilot expansion |
|  |  |  |  |  | Investigate possible funding from CWF and LFO |
|  |  | Develop a formal, system-wide complaints process for survivors |  |  |  |